## Instructions
Guidelines For Completing the Project tracking tool
KEY
Fill in for each monitoring
Fill in AT THE START OF THE PROJECT
Information available in the project proposal or Formulas - DO NOT DELETE/MODIFY !
WHO | The initiation process and preparation of the sheet should start with MEAL staff, then Coordinators take over and fill all required information and planning. Fully participatory process between MEAL and program teams.
WHEN | Monthly for The project workplan, output indicator and beneficiaries database. For the remaining spreadsheets the appropriate frequency is quarterly for long-term projects and bi-monthly or monthly for short projects.
WHY | 1. To enable a systematic follow up of the project's progress towards expected results (activity, indicators, beneficiaries and assumptions) by the coordinators, CEO and M&E 2. To serve as a support for regular project meetings 3. To facilitate project reporting 4. To facilitate the Management team the monitoring of project's progress and challenges at to provide a quick overview which allows for faster feedback
planning sheets | sheets that should be filled once at the beginning of the project
Monitoring sheets | sheets that should be updated regularly after preparation at the planning stage

## Poject Info. Sheet
Project Tracking Tool-NAWA association
Project Code
Project Title
Overall/Principal Objective
Brief Summary about the intervention
Start date |  |  | End date
Project Manager/coordinator |  |  | Duration
Total Budget |  |  | Currency
Donor Share |  |  | Currency
Nawa Share |  |  | Currency
total Direct Beneficiaries planned | 7595
Modification request or Amendement | FALSE |  | Date of MR |  | If Yes, please explain.
Donor
Sectors | Cultural |  |  |  | FALSE
| Artistic |  |  |  | FALSE
| Educational |  |  |  | FALSE
| Psychosocial Support (Mental Health) |  |  | FALSE | TRUE
Implementing partners | INGO |  |  | FALSE
| NGO |  |  | FALSE
| Local Government (Ministries) MoEHE |  |  | FALSE
| CBOs |  |  | FALSE
| UN agencies |  |  | FALSE
Geographical coverage | Deir Al Balah
Target Group (s) | Children- School age |  |  | FALSE
| children pre school |  |  | FALSE
| Parents |  |  | FALSE
| Local Educators |  |  | FALSE
| Nawa Educators |  |  | FALSE
Donor Reporting Requirements | Report # | Reporting period |  | submission date | Responsible
|  | From | To
Donor report 1
Donor report 2
Donor report 3
Donor report 4
Donor report 5
Donor report 6
Donor report 7
Donor report 8
Donor report 9
Donor report 10
Note on G19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: revise Macro checkbox

## Log frame
Title of the Project
| Objectively Verifiable Indicators | Target Value | Sources of Verification | Risks and Assumptions
Overall Impact
Outcome (1)
Output 1.1
Activities 1.1
Output 1.2
Outcome (2)
Output 2.1
Output 2.2
Activities 2.2
Outcome (3)
Output 3.1
Activities 3.1
Output 3.2
Activities 2.2

## Overview Dashboard
|  | Project Start | 0 | Overview Dashboard report |  | Actual progress |  |  | Remaining | this is automatic generated Dash board please don't change focmulas
|  | Project End | 0 |  |  | Time spent (%) |  | #DIV/0! | #DIV/0!
|  | Budget spent | fill it |  |  | Implementation(%) |  | #DIV/0! | #DIV/0!
|  | Duration | fill it |  |  | Budget use (%) |  | #VALUE! | 38%
2020-12-19
Direct Beneficiaries- Overview
| Profile |  |  |  | Activity |  | Activity Progress |  |  | Results' Progress
[7 empty] | Activity 1.1 | #DIV/0! |  | Result 1 | #DIV/0!
|  | 125 |  |  | 8 |  | Activity 1.2 | #DIV/0!
[7 empty] | Activity 1.3 | #DIV/0! |  | Result 2 | #DIV/0!
[5 empty] | 130 |  | Activity 2.1 | #DIV/0!
|  | 425 |  |  |  |  | Activity 2.2 | #DIV/0! |  | Result 3 | #DIV/0!
[5 empty] | 398 |  | Activity 2.3 | #DIV/0!
[7 empty] | Activity 2.4 | #DIV/0!
|  | 8 |  |  | 63 |  | Activity 2.5 | #DIV/0!
[7 empty] | Activity 3.1 | #DIV/0!
[7 empty] | Activity 3.2 | #DIV/0!
Direct Beneficiaries -per Quarter
|  | Quarter 1 |  |  |  | Quarter 2
|  | Quarter 3 |  |  |  | Quarter 4
Direct beneficiaries- per Activity Quarter 1
Direct beneficiaries- per Activity Quarter 2

## Indicator Profile
Results' Level | Intervention Logic | Indicators | Definition | Calculation method | Disaggregation | Baseline Requirements | Data collection Frequency | Reporting Frequency | Means of Verification | Data source | Data collection Method | Sampling | MIS | Lessons Learnt (optional) | Data collection | Data entry | Data verification | Data analysis | Data archiving
Overall Impact
outcomes
Outputs

## Project Work plan
Detailed Implementation Plan | [6 empty] | Period of Action (annual)
Results | Activities | Target |  | Sub Activity (in case) | Status | Responsible Person | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | planned/actual | Progress | 2020-04-04 | 2020-05-04 | 2020-06-04 | 2020-07-04 | 2020-08-04 | 2020-09-04 | 2020-10-04 | 2020-11-04 | 2020-12-04 | 2021-01-04 | 2021-02-04 | 2021-03-04
[7 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 |  |  | Narrative/Comments/Explanations | Narrative/Comments/Explanations | Narrative/Comments/Explanations | Narrative/Comments/Explanations | Narrative/Comments/Explanations | Narrative/Comments/Explanations | Narrative/Comments/Explanations | Narrative/Comments/Explanations | Narrative/Comments/Explanations | Narrative/Comments/Explanations | Narrative/Comments/Explanations | Narrative/Comments/Explanations
|  | unit | value
[5 empty] | Planned | [49 empty] | 1 | 0% | bar: 2021-03-01 W4
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
Actual
[5 empty] | Planned | [50 empty] | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
[5 empty] | Planned | [49 empty] | 0 | #DIV/0!
[5 empty] | Actual | [49 empty] | 0
Activity | Planned Progress | Progress
Activity 1.1 | 100% | #DIV/0!
Activity 1.2 | 100% | #DIV/0!
Activity 1.3 | 100% | #DIV/0!
Activity 2.1 | 100% | #DIV/0!
Activity 2.2 | 100% | #DIV/0!
Activity 2.3 | 100% | #DIV/0!
Activity 2.4 | 100% | #DIV/0!
Activity 2.5 | 100% | #DIV/0!
Activity 3.1 | 100% | #DIV/0!
Activity 3.2 | 100% | #DIV/0!
Overall Project Progress | 100% | #DIV/0!

## Project Tracking Table -PTT
Level | Result | Indicators | Start Date | End date | Baseline |  |  |  | Baseline | Target |  |  |  | Target | Actual |  |  |  | Total | Achievement |  |  |  | Total achieved | Narrative/Comment
[5 empty] | M | FM | CWD M | CWD FM |  | M | FM | CWD M | CWD FM |  | M | FM | CWD M | CWD FM |  | M | FM | CWD M | CWD FM
Overall Objective | [8 empty] | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[9 empty] | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
# of direct BNFS | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Outcomes | [8 empty] | 0 | [5 empty] | 0 |  |  |  |  | #DIV/0!
[9 empty] | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[9 empty] | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[9 empty] | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[9 empty] | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[9 empty] | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[9 empty] | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Outputs | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[9 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[15 empty] | 0 |  |  |  |  | #DIV/0!
[9 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[15 empty] | 0 |  |  |  |  | #DIV/0!
[15 empty] | 0 |  |  |  |  | #DIV/0!
[15 empty] | 0 |  |  |  |  | #DIV/0!
[15 empty] | 0 |  |  |  |  | #DIV/0!
[9 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[9 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[9 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[15 empty] | 0 |  |  |  |  | #DIV/0!
[15 empty] | 0 |  |  |  |  | #DIV/0!

## Output indicators
# | outputs | Indicator | Q1 | [11 empty] | Q2 | [11 empty] | Q3 | [11 empty] | Q4 | [11 empty] | Total Year 1
|  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01
|  |  | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM | M | FM | CWD M | CWD FM
output 1 | [50 empty] | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0
output 2 | [50 empty] | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0
output 3 | [50 empty] | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0
[51 empty] | 0 | 0 | 0 | 0
Note on C7: sara: 75 طفل مستمرين خلال الأشهر وحتى سبتمبر 2020

## Outcome indicators
Level | Indicators | Q1 | [7 empty] | Q2 | [7 empty] | Q3 | [7 empty] | Q4 | [7 empty] | Actual
|  | Numerator |  |  |  | Denominator |  |  |  | Numerator |  |  |  | Denominator |  |  |  | Numerator |  |  |  | Denominator |  |  |  | Numerator |  |  |  | Denominator |  |  |  | % M | % FM | % M (CWDs) | % FM (CWDs)
|  | N-M | N-FM | N-M (CWDs) | N-FM (CWDs) | D-M | D-FM | D-M (CWDs) | D-FM (CWDs) | N-M | N-FM | N-M (CWDs) | N-FM (CWDs) | D-M | D-FM | D-M (CWDs) | D-FM (CWDs) | N-M | N-FM | N-M (CWDs) | N-FM (CWDs) | D-M | D-FM | D-M (CWDs) | D-FM (CWDs) | N-M | N-FM | N-M (CWDs) | N-FM (CWDs) | D-M | D-FM | D-M (CWDs) | D-FM (CWDs)
Overall Objective | [33 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[34 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Outcome | [33 empty] | 0
[34 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[34 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[34 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[34 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[34 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[34 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Beneficiaries Breakdown
1. Beneficiaries Dashboard | [8 empty] | Date Q1
[9 empty] | Date Q2 |  |  |  | Legend | Abbreviation
Project Beneficiaries | [8 empty] | Date Q3 |  |  |  | Nb | Number of beneficiaries
Direct BNFs | 550 | [7 empty] | Date Q4 |  |  |  | BNF | beneficiaries
In Direct BNF | [12 empty] | PWC | People with disability
Total | Sex / Age | Female | Male | CWDs Male | CWDs Female | Children | Youth | Parents | Local Educator | NAWA educator |  |  | Ax | Activity
| Nb of beneficiaries | 125 | 425 | 5 | 3 | 163 | 378 | 398 | 61 | 4 |  |  | Qx | Quarter
| CWDS | 1.455% |  | 20% | 37.5%
PWDs
User Instructions Beneficiaries dashboard is automatic calcution DO NOT change formulas except for MEAL staff Database 2 data entry should be done by project team, MEAL to follow up and ensure accuracy and consistency with MoVs (only UNIQUE BNFs no double counting) Data update should be done on Quarterly basis basis (unless no changes occured on BN numbers) Direct BNFs are those who participate directly in the project, and thus benefit from its existence i.e teachers who attended trainings with Nawa Non-Direct BNFs are those stakeholders who might benefit from direct interaction with Nawa beneficiaires or all those living within the zone of influence of the project (not always the case) i.e teachers (who didn't join the training) but possible interaction with their colleagues who did joined the trainings
Q1 | Sex / Age | Female | Male | CWDs Male | CWDs Female | Children | Youth | Parents | Local Educator | NAWA educator
| Nb of beneficiaries | 40 | 350 | 0 | 3 | 73 | 335 | 335 | 15 | 0
| CWDS | #VALUE!
| PWDs | 15 | 0
Q2 | Sex / Age | Female | Male | CWDs Male | CWDs Female | Children | Youth | Parents | Local Educator | NAWA educator
| Nb of beneficiaries | 50 | 15 | 0 | 0 | 65 | 15 | 25 | 0 | 0
| CWDS | #VALUE!
| PWDs | 5 | 0
Q3 | Sex / Age | Female | Male | CWDs Male | CWDs Female | Children | Youth | Parents | Local Educator | NAWA educator
| Nb of beneficiaries | 15 | 20 | 5 | 0 | 25 | 3 | 18 | 3 | 2
| CWDS | #VALUE!
| PWDs | 3 | 2
Q4 | Sex / Age | Female | Male | CWDs Male | CWDs Female | Children | Youth | Parents | Local Educator | NAWA educator
| Nb of beneficiaries | 20 | 40 | 0 | 0 | 0 | 25 | 20 | 43 | 2
| CWDS | #VALUE!
| PWDs | 2 | 3
Activities | R1 | R2 | R3
Nb of beneficiaries | 8 | 15 | 355
Activity type | Al Khidr library interventions | Schools interventions | Parents activities | Local educator trainings | NAWA educator training
Nb of beneficiaries | 8 | 130 | 398 | 61 | 2
2. Database - only for direct beneficiaries
Q1 Males |  |  | Males | [6 empty] | Males(CWDs) | [6 empty] | Total
RESULT | Activity | Target | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | Male | Males (CWDs)
R1 | Al Khidr library interventions | Children | [14 empty] | 0 | 0
| Schools interventions | low academic achiever children |  |  | 50 | [11 empty] | 50 | 0
R3 | Parents activities | Parents |  |  |  | 100 | 200 | [9 empty] | 300 | 0
| Local educator trainings | Local Educator | [14 empty] | 0 | 0
| NAWA educator training | NAWA educators | [14 empty] | 0 | 0
Total Q1 |  |  | 0 | 0 | 50 | 100 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0
Q1 Females |  |  | Females | [6 empty] | Females (CWDs) | [6 empty] | Total
RESULT | Activity | Target | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | Females | Female (CWDs)
R1 | Al Khidr library interventions | Children |  | 5 | [6 empty] | 3 | [5 empty] | 5 | 3
| Schools interventions | low academic achiever children |  |  | 15 | [11 empty] | 15 | 0
R3 | Parents activities | Parents |  |  |  |  | 20 | [5 empty] | 15 |  |  |  | 20 | 15
| Local educator trainings | Local Educator | [8 empty] | 15 | [5 empty] | 0 | 15
| NAWA educator training | NAWA educators | [14 empty] | 0 | 0
Total Q1 |  |  | 0 | 5 | 15 | 0 | 20 | 0 | 0 | 0 | 18 | 0 | 15 | 0 | 0 | 0 | 40 | 33
Q2 Males |  |  | Males | [6 empty] | Males(CWDs) | [6 empty] | Total
RESULT | Activity | Target | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | Male | Males (CWDs)
R1 | Al Khidr library interventions | Children | [14 empty] | 0 | 0
R2 | Schools interventions | low academic achiever children |  |  |  | 15 | [10 empty] | 15 | 0
R3 | Parents activities | Parents | [9 empty] | 20 |  |  |  |  | 0 | 20
| Local educator trainings | Local Educator | [14 empty] | 0 | 0
| NAWA educator training | NAWA educators | [14 empty] | 0 | 0
Total Q2 |  |  | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 15 | 20
Q2 Females |  |  | Females | [6 empty] | Females (CWDs) | [6 empty] | Total
RESULT | Activity | Target | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | Females | Female (CWDs)
| Al Khidr library interventions | Children | [14 empty] | 0 | 0
| Schools interventions | low academic achiever children |  |  |  |  | 50 | [9 empty] | 50 | 0
| Parents activities | Parents | [12 empty] | 5 |  | 0 | 5
| Local educator trainings | Local Educator | [14 empty] | 0 | 0
| NAWA educator training | NAWA educators | [14 empty] | 0 | 0
Total Q2 |  |  | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 50 | 5
Q3 Males |  |  | Males | [6 empty] | Males(CWDs) | [6 empty] | Total
RESULT | Activity | Target | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | Male | Males (CWDs)
| Al Khidr library interventions | Children | [14 empty] | 0 | 0
| Schools interventions | low academic achiever children |  | 20 | [6 empty] | 5 | [5 empty] | 20 | 5
| Parents activities | Parents | [14 empty] | 0 | 0
| Local educator trainings | Local Educator | [14 empty] | 0 | 0
| NAWA educator training | NAWA educators | [12 empty] | 2 |  | 0 | 2
Total Q3 |  |  | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 2 | 0 | 20 | 7
Q3 Females |  |  | Females | [6 empty] | Females (CWDs) | [6 empty] | Total
RESULT | Activity | Target | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | Females | Female (CWDs)
| Al Khidr library interventions | Children | [14 empty] | 0 | 0
| Schools interventions | low academic achiever children | [14 empty] | 0 | 0
| Parents activities | Parents |  |  |  |  | 15 |  |  |  | 3 | [5 empty] | 15 | 3
| Local educator trainings | Local Educator | [11 empty] | 3 |  |  | 0 | 3
| NAWA educator training | NAWA educators | [14 empty] | 0 | 0
Total Q3 |  |  | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 15 | 6
Q4 Males |  |  | Males | [6 empty] | Males(CWDs) | [6 empty] | Total
RESULT | Activity | Target | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | Male | Males (CWDs)
| Al Khidr library interventions | Children | [14 empty] | 0 | 0
| Schools interventions | low academic achiever children | [14 empty] | 0 | 0
| Parents activities | Parents |  |  |  |  | 20 | [9 empty] | 20 | 0
| Local educator trainings | Local Educator | [5 empty] | 20 | [5 empty] | 3 |  |  | 20 | 3
| NAWA educator training | NAWA educators | [14 empty] | 0 | 0
Total Q4 |  |  | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 40 | 3
Q4 Females |  |  | Females | [6 empty] | Females (CWDs) | [6 empty] | Total
RESULT | Activity | Target | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | 4-6 years | 7 - 10 years | 11- 15 years | 16-18 years | 19- 25 years | 26-40 years | >=41 years | Females | Female (CWDs)
| Al Khidr library interventions | Children | [14 empty] | 0 | 0
| Schools interventions | low academic achiever children | [14 empty] | 0 | 0
| Parents activities | Parents | [14 empty] | 0 | 0
| Local educator trainings | Local Educator | [5 empty] | 20 | [8 empty] | 20 | 0
| NAWA educator training | NAWA educators | [11 empty] | 2 |  |  | 0 | 2
Total Q4 |  |  | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 20 | 2

## MEAL Calendar
No. | Activity | target | Responsibility | Frequency | Achievement Level (%) | planned/Actual | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  | 2020-07-01 |  |  |  | 2020-08-01 |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | Brief Updates | As planned
[7 empty] | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 |  | Delayed activity
1 | Monitoring and Evaluation |  |  |  | #DIV/0! | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Monitoring visits | 5 |  |  | #DIV/0! | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Data collection | 5 | MEAL department | monthly | #DIV/0! | Planned
Actual
| Draft report | 5 | MEAL department | monthly | #DIV/0! | Planned
Actual
| Final report | 4 | MEAL Officer | monthly | #DIV/0! | Planned
Actual
1.2 | Baseline | 2 | MEAL Department | Once a year for new beneficiaries | 0% | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3.1. Development of the tools | 1 | MEAL Officer |  | #DIV/0! | Planned
Actual
| 1.3.2. Data collection | 2 | Project staff |  | #DIV/0! | Planned
Actual
| 1.3.3. Data entry/cleaning | 2 | MEAL department |  | #DIV/0! | Planned
Actual
| 1.3.4. Data analysis | 2 | MEAL department |  | #DIV/0! | Planned
Actual
| 1.3.5. Reporting | 1 | MEAL Officer |  | #DIV/0! | Planned
Actual
1.3 | Endine |  | MEAL Department | Once a year for exit beneficiaries | 0% | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3.1. Development of the tools |  | MEAL Officer |  | 0% | Planned | bar: 2021-03-01 WK4
Actual
| 1.3.2. Data collection |  | Project staff |  | #DIV/0! | Planned
Actual
| 1.3.3. Data entry/cleaning |  | MEAL department |  | #DIV/0! | Planned
Actual
| 1.3.4. Data analysis |  | MEAL department |  | #DIV/0! | Planned
Actual
| 1.3.5. Reporting |  | MEAL Officer |  | #DIV/0! | Planned
Actual
2 | Accountability: Feedback and Complaint Mechanism |  | Not applicable yet | Not applicable yet | #DIV/0! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Developing the Joint feedback/complaint form and setting up Joint complaints and feedback mechanism |  | Not applicable yet |  | #DIV/0! | Planned
Actual
2.2 | Receiving and documenting the complaints and feedback forms in the log sheet |  | Not applicable yet |  | #DIV/0! | Planned
Actual
2.3 | Analyzing the received forms and preparing response letters |  | Not applicable yet |  | #DIV/0! | Planned
Actual
2.4 | Preparing a summary report about the received complaint/feedback forms |  | Not applicable yet |  | #DIV/0! | Planned
Actual
| monthly review meetings |  | Not applicable yet |  | #DIV/0! | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Mid-term Review |  | Not applicable yet |  | #DIV/0! | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | not applicable yet, but NAWA's MEAL department start to conduct project progress meeting with project coordinator monthly from August 2020
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Develop the agenda of the workshop |  | MEAL Department |  | #DIV/0! | Planned
Actual
| Conducting the workshop |  | MEAL Officer |  | #DIV/0! | Planned
Actual
| Issue the first draft of the report |  | Project Coordinator |  | #DIV/0! | Planned
Actual
| Finalize the report |  | MEAL Department/ excutive director |  | #DIV/0! | Planned
Actual
| Prepare management response plan |  | Project Coordinator |  | #DIV/0! | Planned
Actual
4 | Reporting |  |  |  | 50% |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Interim Narrative Report |  | MEAL Officer/ Executive director | semi-annual | 50% | Planned | bar: 2020-04-01 WK4; 2020-10-01 WK4
[6 empty] | Actual | 2020-04-01 WK4: 1; 2020-10-01 WK4: 0
4.2 | Final Narrative Report |  | MEAL Officer/ Executive director | at the end of the project (after five years) | #DIV/0! | Planned
Actual
| Activity |  | Real Progress
| Monitoring visits |  | #DIV/0!
| Baseline |  | 0%
| Endine |  | 0%
| Accountability: Feedback and Complaint Mechanism |  | #DIV/0!
| Mid-term Review |  | #DIV/0!
| Reporting |  | 50%
| Overall progress |  | #DIV/0!
Note on B5: jit: need clarification
Note on D51: sara: conducting monthly meeting with project coordinator for achievment progress

## Assumptions Monitoring
List of assumptions | Mitigation Measures | WAS THE ASSUMPTION FULFILLED? | * IF "NO", OR "ONLY PARTLY", WHICH STRATEGY WAS ADOPTED BY THE PROJECT * IF "YES", NO COMMENT SHOULD BE PROVIDED

## Learning Managment Process
No. | Result | Activity | Source of learning | If "Other", please specify | Recommendation/Learning | Date (when the recommendation was added) | Action | Timing (deadline) | Responsible | Status | Comments
PDM
Monitoring Visit
FGD
Lessons learned exercise
Other